## Slide 1
LEADERSHIP BRIEFING
Bank Agentic AI Platform
Bank_Agentic_Sam — Scrum delivery plan (Jira project BAS)
Saleem | October 2026
Notes: Bank Agentic AI Platform — Bank_Agentic_Sam, team-managed Scrum project BAS in Jira. Start 6 Oct 2026; production target 29 Dec 2026. Sources: workbook 00_START_HERE; Jira import report (bank-agentic-sam-report.md).

## Slide 2
VISION & GOALS
Why we are building a governed agentic AI platform
Bank Agentic AI Platform | Jira project BAS
2
A controlled agent that plans multi-step work and runs banking workflows using only approved tools
Start with high-value, low-risk use cases, backed by measurable success KPIs
One reference architecture: identity, retrieval, tools, governance and observability
Success: v1.0 security-tested, UAT-approved and released to the production population
KEY MESSAGE
Governed, auditable AI for authenticated bank employees, live by 29 Dec 2026.
Notes: Objective and business outcomes from EP-01 (Product Discovery & Architecture) and EP-05 objective; success definition from v1.0 Production release description (07_RELEASES); EP-01 exit criteria: product charter and MVP scope approved, architecture and security boundaries reviewed, DoR/DoD agreed, backlog sprint-ready. EP-02: every interaction tied to an authenticated bank employee. Production target 29 Dec 2026 (00_START_HERE). Source: project workbook (workbook-dump.md).

## Slide 3
SCOPE
Nine epics define the platform scope
Bank Agentic AI Platform | Jira project BAS
3
01
Discovery & Architecture
BAS-1 · Use cases, MVP scope, KPIs and reference architecture
02
Identity & Access
BAS-2 · SSO, entitlements, session isolation, fail-closed access
03
Data & Integrations
BAS-3 · Governed connectors, data contracts and audit logging
04
RAG & Knowledge
BAS-4 · Entitlement-aware retrieval with source citations
05
Agent Orchestration
BAS-5 · Planner, tool registry, human approval for high-risk actions
06
AI Governance
BAS-6 · Prompt-injection defense, PII handling, approval gates
07
LLMOps & Observability
BAS-7 · Evaluation sets, versioning, traces, cost and latency
08
QA, Security & UAT
BAS-8 · Functional, red-team, performance and business UAT testing
09
Release & Adoption
BAS-9 · Phased rollout, runbooks, training, support and adoption
Notes: Full epic names: BAS-1 Product Discovery & Architecture; BAS-2 Identity, Access & User Isolation; BAS-3 Banking Data & System Integrations; BAS-4 RAG & Governed Knowledge; BAS-5 Agent Orchestration & Approved Tools; BAS-6 AI Governance, Privacy & Guardrails; BAS-7 LLMOps, Evaluation & Observability; BAS-8 Quality Engineering, Security & UAT; BAS-9 Production Release, Operations & Adoption. Purposes from workbook 06_EPICS_CREATE scope text; keys from Jira import report.

## Slide 4
DELIVERY APPROACH
Scrum in Jira Cloud: team-managed project BAS, board 235
Bank Agentic AI Platform | Jira project BAS
4
6
Sprints
Two-week sprints, 6 Oct – 28 Dec 2026
3
Releases
v0.1 Foundation, v0.5 Controlled Pilot, v1.0 Production
9
Epics
BAS-1 to BAS-9, one per capability theme
71
Work items
9 epics, 19 stories, 9 tasks, 4 bugs, 30 subtasks
Hierarchy: Epic → Story / Task / Bug → Subtask. Feature = Story + ‘feature’ label; AI Control = Task + ‘ai-control’ label.
Scrum reports: burndown, sprint report and velocity, reviewed during each sprint and at retrospectives.
Notes: Counts from Jira import report (bank-agentic-sam-report.md): 3 versions, 9 epics, 6 sprints (board 235), 71 issues = 9 epics + 19 stories + 9 tasks + 4 bugs + 30 subtasks; 9 dependency links. Features created as Story + 'feature' label; AI Control as Task + 'ai-control' label. Reports (burndown, sprint report, velocity) listed as recommended in workbook 16_JIRA_FEATURES.

## Slide 5
RELEASE ROADMAP
Three releases to production by 29 Dec 2026
Bank Agentic AI Platform | Jira project BAS
5
6–19 Oct 2026
v0.1 Foundation
Approved MVP scope and architecture
SSO identity
User isolation foundation
20 Oct – 30 Nov 2026
v0.5 Controlled Pilot
Governed RAG and agent orchestration
AI guardrails and observability
Ready for controlled pilot
1–29 Dec 2026
v1.0 Production
Security-tested and UAT-approved
Released to the defined production population
Support and escalation active
Notes: Release dates and descriptions from workbook 07_RELEASES and Jira versions in the import report. 'Support and escalation active' is from the EP-09 exit criteria.

## Slide 6
SIX SPRINTS
Six two-week sprints, 6 Oct – 28 Dec 2026
Bank Agentic AI Platform | Jira project BAS
6
S1
6 – 19 Oct
Foundation & Access
Finalize MVP scope, architecture, SSO identity, user-context isolation and the first governed knowledge slice.
S2
20 Oct – 2 Nov
RAG & Knowledge
Governed ingestion, entitlement-aware retrieval, citations and freshness controls.
S3
3 – 16 Nov
Agent Orchestration
Planning, approved tool execution, human approvals and core banking agent workflows.
S4
17 – 30 Nov
Governance & LLMOps
Harden AI guardrails, privacy, observability, evaluation, cost and model/prompt version controls.
S5
1 – 14 Dec
Security QA & UAT
Red-team testing, resilience, defect remediation and business UAT.
S6
15 – 28 Dec
Production & Adoption
Controlled rollout, training, support readiness, adoption measurement and production release.
Notes: Sprint names, dates and goals from workbook 01_MASTER_SEQUENCE and sheets 08_SPRINT1–13_SPRINT6. S6 ends 28 Dec; v1.0 release date is 29 Dec. One backlog item (PB-ST01 / BAS-41) is unscheduled in the backlog.

## Slide 7
BACKLOG AT A GLANCE
71 Jira issues across five work types
Bank Agentic AI Platform | Jira project BAS
7
Work type | Count | Includes | Example in Jira | Used for
Epic | 9 | BAS-1 – BAS-9 | BAS-4 RAG & Governed Knowledge | Business and technology themes
Story | 19 | 10 stories + 9 Features | BAS-14 SSO and session context | User value, with acceptance criteria
Task | 9 | 8 tasks + 1 AI Control | BAS-30 PII masking and retention | Architecture, UAT, standards, operations
Bug | 4 | One each in sprints S2–S5 | BAS-34 Telemetry privacy bug | Reproduction, actual, expected, impact
Subtask | 30 | Created under parent items | BAS-44 Profile API contract | Granular implementation steps
Total | 71 | Plus 9 dependency links | BAS-41 kept for Phase 2 | 
Notes: Counts from Jira import report: 71 issues = 9 epics + 19 stories (incl. 9 Features as Story + label 'feature') + 9 tasks (incl. 1 AI Control as Task + label 'ai-control') + 4 bugs + 30 subtasks; 9 dependency links. Keys from bank-agentic-sam-keymap.json. 'Used for' text from workbook 16_JIRA_FEATURES. BAS-41 (PB-ST01, customer-service case summarization) stays in the product backlog as Phase 2, outside v1.0 (workbook 14_PRODUCT_BACKLOG).

## Slide 8
CRITICAL PATH
Nine dependency links converge on the v1.0 deploy
Bank Agentic AI Platform | Jira project BAS
8
S1 · BAS-14
SSO & session context
Blocks BAS-18 employee profile and entitlement API (S2)
S2 · BAS-18, 20
Governed retrieval
BAS-20 also blocked by critical session-cache bug BAS-16; BAS-21 relates to planner BAS-25
S3 · BAS-26
Human approval
Blocks the v1.0 production deploy BAS-39
S4–S5 · BAS-29, 36
Guardrails, red-team
Prompt-injection defenses block red-team tests; BAS-32 trace evidence relates
S6 · BAS-39
Deploy v1.0
Blocked by BAS-26, UAT sign-off BAS-37 and privacy bug BAS-34
Watch item: BAS-39 cannot ship until human approval (BAS-26), business UAT sign-off (BAS-37) and the telemetry privacy bug (BAS-34) are closed.
Notes: All 9 links from workbook 15_DEPENDENCIES and keymap: BAS-14 blocks BAS-18; BAS-18 blocks BAS-20; BAS-21 relates BAS-25 (step 2 label "Governed retrieval" = BAS-20 Entitlement-Aware Grounded Knowledge Service); BAS-26 blocks BAS-39; BAS-29 blocks BAS-36; BAS-32 relates BAS-36; BAS-37 blocks BAS-39; BAS-16 blocks BAS-20; BAS-34 blocks BAS-39.

## Slide 9
GOVERNANCE
AI controls and review gates built into delivery
Bank Agentic AI Platform | Jira project BAS
9
AI guardrails and privacy (BAS-6, BAS-7)
Prompt-injection defense
Unsafe requests denied and logged (BAS-29)
PII masking and retention
AI Control BAS-30, validated before release
Human-in-the-loop approval
High-risk actions pause for approval (BAS-26)
Audit and trace logging
End-to-end trace IDs and audit correlation (BAS-32)
Assurance and sign-off gates (BAS-8)
Code Review → AI & Security Review
Guardrails, IAM, privacy and RAG/tool safety checked
Red-team and security testing
Adversarial suite BAS-36; evidence retained
Business UAT sign-off
UAT and release-readiness review (BAS-37)
Ready for Release
No unresolved Critical/Highest defects; approval recorded
Planned workflow gates (workbook 04_WORKFLOW) — not yet configured in Jira BAS
Notes: Controls from workbook EP-06/EP-07/EP-08 scope and exit criteria and stories BAS-26, BAS-29, BAS-30, BAS-32, BAS-36, BAS-37. Review gates (Code Review, AI & Security Review, UAT / Validation, Ready for Release) are the recommended enterprise workflow in workbook 04_WORKFLOW. Per the Jira import report, these enterprise statuses are NOT yet configured in Jira project BAS (not settable via the import tool) and remain to be set up.

## Slide 10
RECOMMENDED STRUCTURE
Recommended structure: team and reporting lines
Bank Agentic AI Platform | Jira project BAS
10
Executive Sponsor / Steering Committee
Business owner sign-off
Product Owner
Personas, journeys, backlog priority
Scrum Master
Delivery lead: Ajit Vishwakarma
Architecture & Security
Reference architecture, IAM, controls
Development team
Agent, RAG and integration engineers
QA & Red-team
Testing, adversarial suite
Risk & Compliance
Guardrails, privacy, approvals
LLMOps / Operations
Evaluation, observability, support
Business UAT users
Acceptance and sign-off
Escalation path: Team → Scrum Master → Product Owner → Steering Committee
Notes: RECOMMENDED structure — the workbook has no org chart. Roles drawn from the workbook: Product Owner persona (S1-ST01), business-owner production recommendation (S5 UAT / release-readiness task BAS-37), architecture & security (EP-01, EP-02), QA/red-team and UAT (EP-08), governance/compliance (EP-06), LLMOps/operations (EP-07, EP-09). Ajit Vishwakarma is the assignee on all work items in the workbook (in Jira the assignee lookup failed, so items are unassigned). No other names are given.

## Slide 11
REPORTING CADENCE
Recommended reporting cadence
Bank Agentic AI Platform | Jira project BAS
11
Forum | Cadence | Audience | Output | Jira report
Daily stand-up | Daily | Scrum team | Blockers and impediments | Sprint board
Sprint planning | Start of each 2-week sprint | Team + Product Owner | Sprint goal, committed backlog | Backlog
Sprint review & demo | End of each sprint | PO + stakeholders | Increment demo | Sprint report
Retrospective | End of each sprint | Scrum team | Improvement actions | Velocity
Release / steering status | Per release: v0.1, v0.5, v1.0 | Steering Committee | Release status and risks | Burndown, dashboard
Recommended operating rhythm. Burndown, sprint report, velocity and the management dashboard are listed as “Recommended” Jira features in workbook 16_JIRA_FEATURES.
Notes: Recommended cadence (standard Scrum events for six two-week sprints and three releases). Jira reports (burndown, sprint report, velocity) and the dashboard (Sprint Health, Bugs, Release gadgets) are 'Recommended' in workbook 16_JIRA_FEATURES; the Board is used for the current sprint only.

## Slide 12
RISKS AND NEXT STEPS
Risks to watch and the next steps in Jira
Bank Agentic AI Platform | Jira project BAS
12
TOP RISKS
High
v1.0 deploy (BAS-39) has three blockers: BAS-26, UAT sign-off BAS-37 and privacy bug BAS-34. All are planned in S3–S5.
Med
Prompt injection and privacy defects (BAS-29, BAS-34). Red-team suite BAS-36 must pass before release.
Med
Tight December window: S6 ends 28 Dec and v1.0 releases the next day, 29 Dec.
NEXT STEPS
1
Assign owners: work items are unassigned
2
Tag fixVersions v0.1 / v0.5 / v1.0
3
Configure the review-gate workflow
4
Remove “BAS Sprint 1”; start S1
Notes: Risks from workbook 15_DEPENDENCIES (BAS-26, BAS-37, BAS-34 block BAS-39; BAS-29 blocks BAS-36), sprint dates (S6 15–28 Dec; v1.0 release date 29 Dec). Ratings are the presenter's assessment. Next steps from the Jira import report 'skipped' list: assignee lookup failed (all unassigned); fixVersions not set on issues; enterprise workflow statuses (Code Review, AI & Security Review, etc.) not configured; default sprint 'BAS Sprint 1' (id 202) unused. Then start Sprint S1 (6–19 Oct 2026).